## File Encryptor In C++ - GanttChart.ai
[6 empty] | March 2025 | [25 empty] | April 2025 | [29 empty] | May 2025 | [30 empty] | June 2025 | [29 empty] | July 2025 | [30 empty] | August 2025
Workstream | Task | Team | Duration | Start Date | End Date | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Project Planning
| Define project scope. | Project Management Team | 2 | 2025-03-06 | 2025-03-07
| Research encryption algorithms. | Research Team | 3 | 2025-03-10 | 2025-03-12
| Develop initial project plan. | Project Management Team | 2 | 2025-03-13 | 2025-03-14
| Identify team roles and responsibilities. | Project Management Team | 1 | 2025-03-17 | 2025-03-17
Design and Prototyping
| Design application architecture. | Development Team | 3 | 2025-03-18 | 2025-03-20
| Create wireframes for CLI. | Design Team | 2 | 2025-03-21 | 2025-03-24
| Develop prototype of encryption functionalities. | Development Team | 4 | 2025-03-25 | 2025-03-28
Development
| Implement password-based key encryption algorithm. | Development Team | 3 | 2025-03-31 | 2025-04-02
| Develop file handling functionalities for encrypting and decrypting files. | Development Team | 5 | 2025-04-03 | 2025-04-09
| Create command-line interface (CLI) for user interaction. | Development Team | 4 | 2025-04-10 | 2025-04-15
| Integrate encryption functionalities with CLI. | Development Team | 3 | 2025-04-16 | 2025-04-18
| Refine application based on user feedback. | Development Team | 3 | 2025-05-02 | 2025-05-06
Testing
| Conduct unit tests for encryption and decryption functionalities. | Quality Assurance Team | 3 | 2025-04-21 | 2025-04-23
| Perform integration testing of the complete application. | Quality Assurance Team | 4 | 2025-04-24 | 2025-04-29
Feedback Collection
| Gather user feedback on CLI usability. | User Experience Team | 2 | 2025-04-30 | 2025-05-01
Documentation
| Create user documentation including setup and user guide. | Documentation Team | 4 | 2025-05-07 | 2025-05-12
| Prepare project documentation including design decisions and testing results. | Documentation Team | 3 | 2025-05-13 | 2025-05-15
Project Management
| Conduct final project review and prepare for deployment. | Project Management Team | 2 | 2025-05-16 | 2025-05-19
| Conduct project retrospective and document lessons learned. | Project Management Team | 1 | 2025-05-23 | 2025-05-23
Deployment
| Plan for final deployment of the application. | Deployment Team | 1 | 2025-05-20 | 2025-05-20
Support Planning
| Create post-deployment support and maintenance plan. | Support Team | 2 | 2025-05-21 | 2025-05-22